## Sheet1
|  | 18 |  | 18 |  | 19 |  | 11 |  | 15 | totaal take | 81
| Server | demo | Node And Gateway | demo | Application | demo | Malware | demo | Documentation | demo
1 | set up database | 1 | read NFC tag | 1 | login | 1 | Server send StartRequest | 1 | Architectural requirements | 1
2 | create meeting function | 2 | receive data by NFC | 1 | logout | 1 | Server send stop request | 1 | functional requirements | 1 | punt van completion | take voltooi | kumulatief aftrek | persentasie
3 | add users function (by admin) | 2 | change colour on tap | 1 | store snapshot | 1 | server playback | 1 | user maual | 2 | Begin | 0 | 81 | 100
4 | view meetings | 2 | authenticate email | 2 | load snapshot | 1 | server setup | 1 | Architectural requirements updates | 3 | Demo 1 | 20 | 61 | 75.3086
5 | web gui | 2 | send reply to phone | 2 | validate | 2 | application start Recording | 1 | functional requirements updates | 3 | Demo 2 | 16 | 45 | 55.5556
6 | log in | 3 | integrate node with gateway code | 2 | enable Protection | 1 | Application start Listener | 1 | user maual updates | 3 | Demo 3 | 22 | 23 | 28.3951
7 | log out | 3 | unit test | 3 | get nfc value | 2 | unit test | 2 | Architectural requirements updates | 4 | rest | 14 | 9 | 11.1111
8 | test for administrator | 3 | add light features | 4 | send deviceID | 2 | Application stop recording | 2 | functional requirements updates | 4 | Demo 5 | 6 | 3 | 3.7037
9 | qrcode | 3 | change green if permission | 1 | unit test | 2 | Application implement gui 1 | 3 | user maual updates | 4 | Demo 6 | 3 | 0 | 0
10 | send email to invitee | 3 | change red if no permission | 1 | send email authentication | 3 | Server implement gui | 3 | Architectural requirements updates | 5 |  |  | 0
11 | unit test | 3 | round lights | 3 | encrypt email and password before sending | 3 | prettify gui | 4 | functional requirements updates | 5 |  |  | 0
12 | change user profile | 4 | implement new NFC R/W board | 2 | add extr authentication and incryption | 3 |  |  | user maual updates | 5 |  |  | 0
13 | admin priveledges | 4 | authenticate email and password | 3 | unit test | 3 |  |  | Architectural requirements updates | 6 |  |  | 0
14 | unit test | 4 | check user in on server | 4 | continuous checking connections | 3 |  |  | functional requirements updates | 6 |  |  | 0
15 | unit test | 4 | unlock door | 5 | gui | 4 |  |  | user maual updates | 6
16 | unit test | 4 | strip lights | 2 | gui that connects to server | 4
17 | web gui follow up | 3 | integrate node with gateway physically | 3 | log in | 4
18 | plan database | 1 | integrate gateway with server | 3 | create meeting | 5
19 |  |  |  |  | show list meeting | 5
20
21
22