## Sheet1
|  | 18 |  | 18 |  | 19 |  | 11 |  | 15 | totaal take | 80
| Server | demo | Node And Gateway | demo | Application | demo | Malware | demo | Documentation | demo
1 | set up database | 1 | read NFC tag | 1 | login | 1 | Server send StartRequest | 1 | Architectural requirements | 1
2 | create meeting function | 2 | receive data by NFC | 1 | logout | 1 | Server send stop request | 1 | functional requirements | 1 | punt van completion | take voltooi | kumulatief aftrek | persentasie
3 | add users function (by admin) | 2 | change colour on tap | 1 | store snapshot | 1 | server playback | 1 | user maual | 2 | Begin | 0 | 80 | 100
4 | view meetings | 2 | authenticate email | 2 | load snapshot | 1 | server setup | 1 | Architectural requirements updates | 3 | Demo 1 | 20 | 60 | 75
5 | web gui | 2015-05-12 | send reply to phone | 2 | validate | 2 | application start Recording | 1 | functional requirements updates | 3 | Demo 2 | 15 | 45 | 56.25
6 | log in | 3 | integrate node with gateway code | 2 | enable Protection | 1 | Application start Listener | 1 | user maual updates | 3 | Demo 3 | 22 | 23 | 28.75
7 | log out | 3 | unit test | 3 | get nfc value | 2 | unit test | 2 | Architectural requirements updates | 4 | rest | 14 | 9 | 11.25
8 | test for administrator | 3 | add light features | 4 | send deviceID | 2 | Application stop recording | 2 | functional requirements updates | 4 | Demo 5 | 6 | 3 | 3.75
9 | qrcode | 3 | change green if permission | 1 | unit test | 2 | Application implement gui 1 | 3 | user maual updates | 4 | Demo 6 | 3 | 0 | 0
10 | send email to invitee | 3 | change red if no permission | 1 | send email authentication | 3 | Server implement gui | 3 | Architectural requirements updates | 5 |  |  | 0
11 | unit test | 3 | round lights | 3 | encrypt email and password before sending | 3 | prettify gui | 4 | functional requirements updates | 5 |  |  | 0
12 | change user profile | 4 | implement new NFC R/W board | 2 | add extr authentication and incryption | 3 |  |  | user maual updates | 5 |  |  | 0
13 | admin priveledges | 4 | authenticate email and password | 3 | unit test | 3 |  |  | Architectural requirements updates | 6 |  |  | 0
14 | unit test | 4 | check user in on server | 4 | continuous checking connections | 3 |  |  | functional requirements updates | 6 |  |  | 0
15 | unit test | 4 | unlock door | 5 | gui | 4 |  |  | user maual updates | 6
16 | unit test | 4 | strip lights | 2 | gui that connects to server | 4
17 | web gui follow up | 3 | integrate node with gateway physically | 3 | log in | 4
18 | plan database | 1 | integrate gateway with server | 3 | create meeting | 5
19 |  |  |  |  | show list meeting | 5
20
21
22

## Sheet3
Estimated remainig hours |  |  |  | 389 | 373.4 | 357.9 | 342.3 | 331.8 | 369.6 | 351.1 | 332.6 | 314.2 | 295.7 | 290.4 | 271 | 272 | 251 | 253.4 | 232.8 | 210.6 | 200.6 | 175.6 | 150.5 | 125.4 | 100.3 | 75.2 | 50.2 | 25.1 | 0
Cumelative sum of hours |  |  |  |  | 42 | 111 | 140 | 146 | 156 | 162 | 164 | 169 | 197 | 224 | 252 | 311 | 334 | 359 | 387 | 451 | 461 | 485 | 508 | 516 | 516 | 516 | 516 | 516 | 516
Actual remaining hours |  |  |  |  | 389 | 347 | 278 | 255 | 316 | 306 | 300 | 298 | 293 | 287 | 260 | 271 | 212 | 242 | 223 | 198 | 176 | 166 | 142 | 119 | 111
total tasks @ point in time |  |  |  |  | 389 | 389 | 389 | 395 | 462 | 462 | 462 | 462 | 462 | 484 | 484 | 523 | 523 | 576 | 582 | 585 | 627 | 627 | 627 | 627 | 627 | 627 | 627 | 627 | 627
[5 empty] | 1 |  | Demo 1 | [9 empty] | Demo 2 |  |  |  | Demo 3 |  |  | Demo 4 |  |  |  | Demo 5 | Project day
| Task | added date | Total hours | Estimated hours | 2015-05-08 | 2015-05-15 | 2015-05-22 | 2015-05-29 | 2015-06-05 | 2015-06-12 | 2015-06-19 | 2015-06-26 | 2015-07-03 | 2015-07-10 | 2015-07-17 | 2015-07-24 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-21 | 2015-08-28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23
Server | Set Up Database | 2015-05-12 | 9 | 9 | 2015-05-15: 1; 2015-05-22: 4; 2015-07-24: 2; 2015-07-31: 1; 2015-08-14: 1
Server | code create_meeting function | 2015-05-12 | 6 | 6 | 2015-07-10: 2; 2015-07-17: 3; 2015-07-31: 1
Server | code add_user function | 2015-05-12 | 7 | 6 | 2015-07-10: 1; 2015-07-17: 3; 2015-07-24: 1; 2015-08-07: 1; 2015-08-14: 1
Server | Database discussion | 2015-05-12 | 9 | 2 | 2015-05-08: 1; 2015-05-15: 1; 2015-05-22: 1; 2015-07-17: 1; 2015-08-21: 1; 2015-08-28: 2; 2015-09-04: 2
Server | code log in function | 2015-05-12 | 5 | 4 | 2015-09-04: 1; 2015-09-11: 3; 2015-09-18: 1
Server | code log out function | 2015-05-12 | 4 | 4 | 2015-09-11: 3; 2015-09-18: 1
Server | code registration | 2015-05-12 | 4 | 4 | 2015-09-11: 3; 2015-09-18: 1
Server | research QR code | 2015-05-12 | 4 | 6 | 2015-09-11: 4
Server | code test_for_admin | 2015-05-12 | 0 | 3
Server | create web interface meeting | 2015-05-12 | 8 | 9 | 2015-07-24: 5; 2015-07-31: 1; 2015-08-14: 1; 2015-08-21: 1
Server | create web interface log in | 2015-05-12 | 2 | 5 | 2015-09-18: 2
Server | create web interface register | 2015-05-12 | 3 | 5 | 2015-09-18: 3
Server | code add_user_to meeting | 2015-05-12 | 9 | 7 | 2015-07-17: 2; 2015-07-24: 3; 2015-08-21: 4
Application | code login | 2015-05-12 | 6 | 6 | 2015-05-08: 6
Application | code logout | 2015-05-12 | 4 | 6 | 2015-05-08: 4
Application | code store_snapshot | 2015-05-12 | 3 | 5 | 2015-05-15: 3
Application | code load_snapshot | 2015-05-12 | 3 | 4 | 2015-05-15: 3
Application | code validate | 2015-05-12 | 8 | 5 | 2015-05-15: 1; 2015-05-22: 0; 2015-05-29: 1; 2015-06-05: 1; 2015-06-12: 5
Application | research turning features of and on | 2015-05-12 | 13 | 12 | 2015-05-15: 5; 2015-05-29: 4; 2015-06-05: 2; 2015-06-19: 2
Application | write unit tests | 2015-05-12 | 12 | 10 | 2015-05-15: 2; 2015-07-17: 2; 2015-07-24: 3; 2015-08-21: 5
Application | code Enable Protection | 2015-05-12 | 10 | 15 | 2015-05-15: 5; 2015-05-22: 5
Application | code getnfc value | 2015-05-12 | 11 | 10 | 2015-05-22: 1; 2015-05-29: 1; 2015-06-26: 5; 2015-07-03: 2; 2015-07-31: 2
Application | GUI connect to server | 2015-05-12 | 5 | 2 | 2015-09-04: 5
Node and Gateway | get to read NFC tag | 2015-05-12 | 11 | 9 | 2015-05-08: 3; 2015-05-15: 2; 2015-07-03: 4; 2015-07-10: 2
Node and Gateway | get to receive data from NFC | 2015-05-12 | 11 | 12 | 2015-05-15: 4; 2015-07-17: 6; 2015-07-24: 1
Node and Gateway | send reply to phone | 2015-05-12 | 9 | 9 | 2015-07-10: 9
Node and Gateway | integrate node with gate | 2015-05-12 | 9 | 8 | 2015-07-10: 9
Node and Gateway | implement new NFC R/W board | 2015-05-12 | 12 | 12 | 2015-07-17: 2; 2015-07-24: 5; 2015-07-31: 5
Node and Gateway | check user in on server | 2015-05-12 | 0 | 6
Node and Gateway | unlock door | 2015-05-12 | 0 | 6
Node and Gateway | integrate node with gateway physically | 2015-05-12 | 0 | 6
Node and Gateway | integrate gateway with server | 2015-05-12 | 0 | 13
Malware | code Server send StartRequest | 2015-05-12 | 9 | 13 | 2015-05-08: 3; 2015-05-15: 6
Malware | code Server send stop request | 2015-05-12 | 3 | 13 | 2015-05-08: 3
Malware | code server playback | 2015-05-12 | 4 | 8 | 2015-05-08: 3; 2015-05-15: 1
Malware | code server setup | 2015-05-12 | 3 | 6 | 2015-05-08: 3
Malware | code application start Recording | 2015-05-12 | 4 | 8 | 2015-05-08: 3; 2015-05-15: 1
Malware | code Application start Listener | 2015-05-12 | 4 | 8 | 2015-05-08: 3; 2015-05-15: 1
Malware | code Application stop recording | 2015-05-12 | 11 | 12 | 2015-05-15: 1; 2015-05-22: 2; 2015-06-05: 7; 2015-06-12: 1
Malware | code Application implement gui | 2015-05-12 | 9 | 11 | 2015-07-03: 8; 2015-07-10: 1
Malware | prettify gui | 2015-05-12 | 0 | 11
Malware | reseach recording | 2015-05-12 | 6 | 12 | 2015-05-08: 3; 2015-05-15: 3
Malware | research android programming | 2015-05-12 | 23 | 15 | 2015-05-08: 7; 2015-05-15: 7; 2015-07-03: 7; 2015-07-24: 2
Documentation | Architectural requirements Malware | 2015-05-12 | 19 | 20 | 2015-05-15: 3; 2015-05-22: 2; 2015-07-24: 4; 2015-07-31: 2; 2015-08-21: 7; 2015-09-11: 1
Documentation | Functional requirements Malware | 2015-05-12 | 18 | 20 | 2015-05-15: 3; 2015-05-22: 2; 2015-07-24: 5; 2015-08-21: 7; 2015-09-11: 1
Documentation | User maual Malware | 2015-05-12 | 11 | 6 | 2015-05-22: 0; 2015-07-24: 1; 2015-07-31: 4; 2015-08-21: 2; 2015-08-28: 3; 2015-09-11: 1
Documentation | Architectural requirements EPIC | 2015-05-12 | 19 | 22 | 2015-05-15: 3; 2015-05-22: 2; 2015-07-24: 6; 2015-08-21: 7; 2015-09-11: 1
Documentation | Functional requirements EPIC | 2015-05-12 | 21 | 21 | 2015-05-15: 3; 2015-05-22: 7; 2015-07-24: 3; 2015-08-21: 7; 2015-09-11: 1
Documentation | User maual EPIC | 2015-05-12 | 10 | 12 | 2015-05-22: 0; 2015-07-31: 5; 2015-08-21: 2; 2015-08-28: 2; 2015-09-11: 1
Application | create GUI | 2015-05-29 | 10 | 9 | 2015-07-03: 2; 2015-07-10: 3; 2015-08-14: 5
Node and Gateway | get to change colour on tap | 2015-06-05 | 6 | 5 | 2015-05-15: 1; 2015-05-22: 2; 2015-07-24: 3
Node and Gateway | add light features | 2015-06-05 | 8 | 9 | 2015-05-15: 7; 2015-05-22: 1
Node and Gateway | get to change green in permission granted | 2015-06-05 | 4 | 3 | 2015-07-17: 2; 2015-07-24: 2
Node and Gateway | get to change red if no permission | 2015-06-05 | 4 | 3 | 2015-07-17: 2; 2015-07-24: 2
Node and Gateway | program strip lights | 2015-06-05 | 9 | 9 | 2015-07-17: 5; 2015-07-24: 4
Node and Gateway | program round lights | 2015-07-05 | 9 | 9 | 2015-08-14: 9
Server | unit test all | 2015-07-24 | 9 | 10 | 2015-07-24: 5; 2015-08-21: 2; 2015-09-11: 2
Server | integration test all | 2015-07-24 | 6 | 5 | 2015-07-24: 2; 2015-08-21: 2; 2015-09-11: 2
Node and Gateway | unit test all | 2015-07-24 | 9 | 10 | 2015-05-15: 1; 2015-08-07: 7; 2015-08-14: 1
Malware | unit test all | 2015-07-24 | 11 | 10 | 2015-05-15: 1; 2015-07-31: 2; 2015-08-07: 5; 2015-09-04: 3
Application | code send deviceID | 2015-08-07 | 5 | 5 | 2015-09-04: 5
Application | prettify GUI | 2015-08-07 | 2 | 9 | 2015-09-04: 2
Application | add extra authentication and incryption | 2015-08-07 | 5 | 5 | 2015-08-14: 5
Application | encrypt email and password before sending | 2015-08-07 | 5 | 4 | 2015-07-03: 5
Server | code change_user_profile_function | 2015-08-08 | 0 | 5
Malware | code Server implement gui | 2015-08-08 | 17 | 15 | 2015-08-14: 1; 2015-08-21: 7; 2015-08-28: 3; 2015-09-04: 6
Application | code continuous checking connections | 2015-08-14 | 7 | 7 | 2015-08-14: 2; 2015-08-21: 5
Server | code send_email_on_invite | 2015-08-21 | 7 | 6 | 2015-08-14: 2; 2015-08-21: 5
Application | create read QR-Code | 2015-09-04 | 0 | 15
Application | code add meeting to phones meeting list | 2015-09-04 | 0 | 12
Application | code encrypt email and password before sending | 2015-09-04 | 5 | 6 | 2015-08-07: 5
Node and Gateway | authenticate email | 2015-09-04 | 7 | 7 | 2015-08-07: 7
Node and Gateway | authenticate email and password | 2015-09-04 | 0 | 5